## 1. Product Overview
Item | Description
Product Name | AI BASED PNEUMONIA DETECTION
Product Vision/ Purpose | To empower healthcare professionals with fast, accurate, and accessible AI-driven pneumonia detection to enhance patient care everywhere.
Business Goals / Key Success factors | To secure adoption in small-to-medium hospitals by delivering an accurate, integrated AI solution that improves diagnostic speed, reduces radiologist workload, and enhances patient outcomes
Primary Stakeholders | Primary stakeholders are the key decision-makers: Radiologists, Hospital Administrators, Medical Directors, and CTOs of HealthTech Companies

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | Technical Requirements | Priority (MoSCoW) | Status | Owner | Test Owner
| Major features | Mandatory |  |  | Mandatory | Mandatory | Mandatory
E1 | BACKEND | US1 | Set up FastAPI backend with all required routes. | Must Have | DONE | sriram | roja
|  | US2 | Build /predict API endpoint for image upload and model inference. | Must Have | DONE | shiva | sharanya
|  | US3 | Preprocess X-ray images before prediction. | Must Have | DONE | sriram | roja
|  | US4 | Add CORS support for frontend–backend communication. | Must Have | DONE | shiva | sharanya
|  | US9 | Add Transfer Learning Model RESNET by freezing some 80 layers | Must Have | DONE | Roja | shiva
|  | US11 | Data Augmentation( improve accuracy) | Must Have | DONE | Roja | shiva
E2 | FRONTEND | US5 | Design the Home, Upload, Results, Login, and History pages | Should Have | DONE | roja | sriram
|  | US6 | Implement drag-and-drop X-ray image upload. | Should Have | DONE | sharanya | shiva
|  | US7 | Display prediction output clearly (Normal/Viral/Bacterial). | Should Have | DONE | roja | sriram
|  | US8 | Implement dark/light mode option | Should Have | DONE | sharanya | shiva
TEST PLAN AND TEST RESULTS
Epic ID | Module | Test Case ID | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Test Owner
E1 | BACKEND | TC1 | Test FastAPI backend initialization | Start server & hit /health route | Server should respond with 200 OK | Working as expected | PASSED | Roja
E1 | BACKEND | TC2 | Test /predict API upload | Upload valid X-ray image | API returns prediction + confidence score | Working as expected | PASSED | Sharanya
E1 | BACKEND | TC3 | Test image preprocessing | Submit raw X-ray image | Preprocessed output (normalized + resized) | Function working correctly | PASSED | Shiva
E1 | BACKEND | TC4 | Test CORS policy | Send request from frontend domain | API should accept request | Working as expected | PASSED | Shiva
E1 | BACKEND | TC5 | Test RESNET integration | Send image for inference | Model loads + returns result | Model integrated | PASSED | Roja
E2 | FRONTEND | TC7 | Test UI page navigation | Navigate Home → Upload → Result | All pages load smoothly | Works as expected | PASSED | Sharanya
E2 | FRONTEND | TC8 | Test drag-and-drop upload | Drag image into upload box | Image preview should appear | Works as expected | PASSED | Shiva
E2 | FRONTEND | TC9 | Test result display | Upload image and wait for API response | Normal/Viral/Bacterial displayed clearly | Works correctly | PASSED | Sriram
E2 | FRONTEND | TC10 | Test dark/light mode | Toggle theme | UI switches consistently across pages | Works correctly | PASSED | Sharanya
E1/E2 | FULL SYSTEM | TC11 | End-to-End testing | Upload X-ray image from frontend | Backend predicts & frontend displays | End-to-end flow working | PASSED | Sriram

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | Authentication, Dashboard MVP | None | Done
v0.2 | 2025-11-22 | Analytics export, Notification system | Requires API upgrade | Done
v0.3 | 2025-11-29 | Design the Home, Upload, Results, Login, and History pages | Backend API endpoints must be stable & accessible | Done
v0.4 | 2025-12-06 | Preprocess X-ray images before prediction. | Requires model preprocessing pipeline + image handling API | Done
v0.5 | 2025-12-13 | Display prediction output clearly (Normal/Viral/Bacterial). | Requires /predict API functioning + model inference response | Done
v1.1 | 2025-12-27 | Add Transfer Learning Model RESNET by freezing some 80 layers | Requires GPU/compute setup + dataset cleaned & prepared | Done

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items (Next Time) | Owner
Authentication and Dashboard MVP were implemented smoothly | Minor UI inconsistencies during integration | Standardize UI components & create reusable layouts | Frontend Lead
Analytics export + Notification system API upgrade started | API upgrade took longer than expected | Lock API requirements before sprint start | Backend Lead
Home, Upload, Results, Login, and History pages designed well | Design review cycles took time | Freeze UI wireframes earlier | Frontend Lead
Image preprocessing pipeline working correctly | Optimization for large images pending | Add batch preprocessing & caching | Backend Lead
Prediction output displayed clearly (Normal / Viral / Bacterial) | Prediction response structure changed mid-sprint | Use fixed API versioning | Backend Lead